## PIS customization
No. of days | No. of Hours | Customization Details | Brief Description | Comments from Vanuston | New customization request from Mymedicine | Date of completion
5 | 40 | Multiple image in proudct details | Add multiple images (3-4 images) per product in Product detail | 3 images per product in Product Detail - Provision for 4th image will be added as well | - | 2022-01-17
5 | 40 | Description (bilingual) in product data | Required field for Product Description (Some fields are already exist in the MEDEIl system, but all text boxes need two - English and Myanmar) - Selling Unit (UOM)- english and myanmar - Package Size-english and myanmar - Manufacturer Name- only english - Made In (Country)- only english - Chemical Name (Generic) - only english - Action and Indication -english and myanmar - Dosage-english and myanmar - Potential side Effects -english and myanmar - Product Information-english and myanmar | Product Information field is mentioned for bilingual entry | Package Size, Made in (Country),Action and Indication, Dosage, Potential Side Effects are new fields need to be added in the Product Master apart from Product Information. Please confirm if Fields such as Action & Indication, Potential Side effects, Product information are the only fields required for Bilingal inputs? | 24-01-2022 - addition 3 days will be added for the new customization fields | All the fields need myanmar language provision- Lae will confirm Mfg name, made in country, chemical name
4 | 32 | Enable SKU code in product data | Generate SKU Code automatically for each product - 8 digits - Auto genearted (auto increase) - Append - First 2 digit - Group ID - Second 2 digit - SubGroup ID - Last 4 digit - Product ID (auto generate) SKU code master Group - Group Name - Group ID (Starting from 01, auto increase) Sub Group - Sub Group Name - Group Name (Group name retrieved with dropdown) - Sub Group ID (Staring from 01, auto increase) | Enable manual SKU Code in product data | New Group ID , New Group name, New Sub Group Name, New Sub group ID should be created in the Product Master apart from SKU Code | 3-02-2022 - addition of 4 days will be added for the new customization
15 | 120 | Good Receive Note flow after purchase | - When deliver medicine from suppliers, Operation team will create Good Receive Note form to mark as received - After Good Receive Note is done, inventory will be updated with delivered items - Refer to GRN sheet for Good Receive Note form format GRN,PO and PR Format | GRN form will be done as mentioned
6 | 48 | Enable multi payment method (Bank, Cash, KBZPay) in purchase and sales | Payment Method Add (dropdown list) - should be created in PO form for input, Sales only as it is. -- Bank - Cash On Delivery - KBZPay - Consignment | Sales Form -Payment options will be replaced with the list given . Regarding purchase form - we would like to clarify if it is required in the payment form while making the payment to the vendor |  | 2022-02-09
3 | 24 | Show Auto generated Vendor Code | - Add a new textbox for "Vendor Code" field on creating new Vendor - Auto retrieve Vendor Code when choosing Vendor name on PO, PR and GRN forms | Auto generated Vendor Code will be created new in New Vendor registration Auto Retrieve as mentioned in PO, PR n GRN forms |  | 2022-02-15
10 | 80 | Enable Purchase Request from HQ before Purchase Order | - Refer to PR sheet for Purchase Request form format GRN, PO and PR Format | PR form will be created as mentioned | Fields like Balance, Consumption quantity should be autogenerated. Request Area, Request Date and Expected Delivery date should be created for input fields | Print option will be given in the View form-user names printed automatically - Expected delivery date input need to be given by Lae
5 | 40 | Tax Calculation setting as per Myanmar Tax rules | Sit with Finance team for detail when setup Myanmar Taxation setting | yet to discuss about commercial tax and its calculation part
10 | 80 | Purchase Order Approval form | - Refer to PO sheet for Purchase Order form format GRN, PO and PR Format | PO form will be created as mentioned | Delivery Area My Medicine Ware House,Contact name and Contact no should be given as input field, also Total amount including CT( commercial tax) calculation need briefing from Finance team
7 | 56 | Reports such as Vendor-wise Outstanding Payments, Weighted Average Cost Calculation report Inventory Aging Reports, Customer Ledger Account report with Balance to be shown | Report Sample for PIS - Google Docs | 1. Customer Ledger Account report- will be customized as mentioned 2.Inventory Valuation Report - will be customized as mentioned 3. Inventory on hand(current stock) report -SKU code, SKU name, UOM, Batch, on Hand Qty,Expiry fields are clear but pls clarify about Relation, Location, Lot 4. In Inventory aging Report- Batch and lot no given in two fields but we have only Batch no. in medeil- hence require briefing for Lot no., also the calculations of each part of days period 5. Vendor Account Statement(Vendor Ledger) Report is clear and will be customized as mentioned 6. Vendor Balance List -Need clarification on the calculations 7. Vendor Aging Report- it is clear and will be done as mentioned 8. PO Report - you have given 32 fields which cannot be given in a single report- so kindly recheck and let us know which fields are required for PO report
|  | Sales reports – Daily sales report with all products with few fields like username , Customer mobile no | Report Sample for PIS - Google Docs | Sales Order Report -pls refer the queries mentioned in the next column in this form | 1. Sales Order Report / Sales Register - Categories, Shipping Fee, Calculation of Net Sales, CTS, Net Revenue - field need breifing where these field values and calculation will be done
|  | Delivery Charges to be added to the Sales invoice Form |  |  | Delivery Charges to be added to the Sales invoice Form
2 | 16
72 | 576

## Purchase Requisition
[10 empty] | Item Code | Product Code
[10 empty] | Item Name | Product Name
[10 empty] | Balance | Existing Inventory Balance
Purchase Requisition Form | [9 empty] | ConsumptionQty | Last month sale count
PR.No.
[8 empty] | Requested Date: |  | In the system, we limit the access of who can create PR, who can acknowledge and who can approve.
[8 empty] | Requested Area: |  | Only those persons have access to edit and approve.
We log the users activities, and show the user info as PR request person, PR acknowledge person, PR approve person.
Sr. | Item Code | Item Name | Supplier | UOM | Qty | Balance | Consumption Qty (1 month Backward) | Expected Delivery Date | Remark
[10 empty] | Requested area | Warehouse names | List of warehouse name
expected delivery date should in grid
| Requested by, |  |  | Acknowledged by, |  |  |  | Approved by,
Sign: |  |  |  | Sign: |  |  |  | Sign:
Name: |  |  |  | Name: |  |  |  | Name:
Date: |  |  |  | Date: |  |  |  | Date:
Cost centre No.

## PO
[14 empty] | Item Code | Product Code
[14 empty] | Item Name | Product Name
[14 empty] | FOC | FOC number get from supplier, it will be added in inventory update, and cost calculation
In the system, we limit the access of who can create PO, who can acknowledge and who can approve.
Purchase Order Form | [13 empty] | Only those persons have access to edit and approve.
[10 empty] | Order Date : |  |  |  | We log the users activities, and show the user info as PO request person, PO acknowledge person, PO approve person.
PO No. | [9 empty] | Expected Delivery Date :
Supplier : Supplier Code: Contact Person : Contact No. | [9 empty] | Delivery Area My Medicine Ware House Contact Person Contact No. |  |  | Warehouse contact person
Sr.No. | Item Code | Description | UOM | Qty | Unit Price | Currency | FOC | Discount % | Discount Amount | Amount | Total Amount Including CT | Remark |  |  | unit price is Box Price
[9 empty] | - | - | - |  |  |  | we need only the Box Price
[9 empty] | - | - | - |  |  |  | Currency - Lae will confirm
[9 empty] | - | - | - |  |  |  | FOC -Free Quantity
[9 empty] | - | - | - |  |  |  | Sample PO - Lae
[9 empty] | - | - | - |  |  |  | Discount % and Discount amount are different for each product
[9 empty] | - | - | - |  |  |  | PO form also carries approval , acknowledge status like PR form
[9 empty] | - | - | - |  |  |  | Total amt, disccount, net amount to be added
[9 empty] | - | - | -
[9 empty] | - | - | -
[9 empty] | - | - | -
Total amount:
Discount :
| Submitted By : |  | Acknowledged By : | [5 empty] | Approved By : | Net Amount :
Sign |  |  | Sign |  |  |  |  | Sign
Name |  |  | Name |  |  |  |  | Name
Date |  |  | Date |  |  |  |  | Date
Comment (Payment terms & Tax, and other information etc..)

## GRN
Good Received Note
GRN No : PO No :
Currency
Exchange Rate
[10 empty] | Received Date: Due Date: |  |  |  | Item Code | Product Code
Supplier Name : Supplier Code : Supplier Contact : | [9 empty] | Delivered To : |  |  |  | Item Name | Product Name
[14 empty] | FOC | FOC number get from supplier, it will be added in inventory update, and cost calculation
[14 empty] | Pack size | Delivered pack size
Invoice No (provided by supplier) :
Sr. | Item Code | Item Name | Pack size | UOM | Batch No/ Lot No | Exp Date | Qty | Unit Price | FOC | Discount % | Discount Amount | Total Amount | Remark | In the system, we limit the access of who can receive goods, who can acknowledge and who can approve.
1 | 10102 | Sample A |  |  |  |  | 5 | 500 | 1 | 10% | 250 | 2250 |  | Only those persons have access to edit and approve.
We log the users activities, and show the user info as GRN request person and GRN acknowledge person
Pack size is required in the GRN form - confirmed by Lae
Total Amount :
Discount :
Net Amount :
| Prepared by, |  |  |  |  | Acknowledged by,
Sign | [5 empty] | Sign
Name | [5 empty] | Name

## Reports Sample
Customer Detail Statement
Sale Order Report/ Sale Register
Inventory Valuation Report
ok
Inventory on hand report
ok
Inventory Aging Report
Vendor Account Statement
ok
Vendor Balance List
complete
Vendor Aging Report
PO report
We would like to include below columns in the PO Report as horizontal,
Vendor
Vendor Name
Actual Vendor Name
Purchase order
GRN No.
GRN Date
GRN Voucher
Item
Item Name
Old Item
Purch UOM
Unit Price
Discount
Discount (%)
Currency
Ordered Qty
Qty Received
Remain Qty
Receipt Amount
Invoice
Invoice Date
Internal Voucher
Invoice description
Invoiced Qty
Tax Amount
Line Amount
Invoiced Amount(W/O Header Disc)
Header Disc Per
Header Disc Amount
Warehouse
Invoice Amount
PO Print on PDF
8